## Sheet1
Risk ID | Risk Description | Asset/Service | TSC | Likelihood | Impact | Inherent Score | Key Control(s) | Owner | Status | Inherent Risk Score | Key Controls
R-001 | Unauthorized access to S3 objects | S3 | CC6.1, CC7.2 | 3 | 5 | 15 | S3 Block Public Access, SSE-KMS, IAM least privilege | SCE | Open
R-002 | Privilege creep in IAM roles/users | IAM | CC6.1 | 4 | 4 | 16 | RBAC, IAM Access Analyzer, periodic reviews | CPA | Open
R-003 | CloudTrail disabled or tampered | CloudTrail | CC7.2 | 3 | 5 | 15 | Org trail enabled, log file validation, alarms | SCE | Open
R-004 | Data unencrypted at rest | S3/EBS/RDS | CC6.7 | 2 | 5 | 10 | Default encryption + KMS CMKs | CPA | Open
R-005 | Exposed ports in VPC security groups | VPC/EC2 | CC6.6 | 4 | 4 | 16 | Restricted SGs, Config rule restricted-ssh | CPA | Open
R-006 | No monitoring of unauthorized API calls | CloudWatch | CC7.2, CC7.3 | 3 | 4 | 12 | Metric filters, CloudWatch Alarm + SNS alerts | SCE | Open
R-007 | Configuration drift and unauthorized changes remain undetected, leading to non-compliance and increased exposure of sensitive data. | AWS Config | CC8.1 | 3 | 4 | 12 | Enable AWS Config across all accounts/regions, implement drift detection rules (encryption, no public S3, restricted SSH), review compliance dashboard. | CPA | Open
R-008 | Absence of GuardDuty threat detection may allow unauthorized activity, malware, or data exfiltration to go unnoticed. | GuardDuty | CC7.3 | 3 | 5 | 15 | Enable GuardDuty in all regions, review findings regularly, escalate/triage alerts. | SCE | Open